## ActionItems
YMCA of the Palm Beaches Constraints Log
DUE IN 8 DAYS+
[8 empty] | DUE IN NEXT 7 DAYS |  | LAST UPDATED: | 2023-06-27
[8 empty] | DATE PAST DUE |  | NEXT MEETING: | 2023-06-27
No # | DESCRIPTION | DATE IDENTIFIED | DAYS ELAPSED | REFERENCE | CLOSURE DOCUMENT | ASSIGNED | B.I.C | DUE | COMPLETION DATE | STATUS | COMMENTS
1. PERMITS
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
1.16
1.17
1.18
1.19
1.2
1.21
1.22
1.23
1.24
1.25
1.26
1.27
1.28
1.29
1.3
1.31
1.32
1.33
1.34
1.35
1.36
1.37
1.38
1.39
1.4
1.41
1.42
1.43
1.44
1.45
1.46
1.47
1.48
1.49
1.5
1.51
1.52
1.53
1.54
1.55
1.56
1.57
1.58
1.59
1.6
1.61
1.62
1.63
1.64
1.65
1.66
1.67
1.68
1.69
1.7
1.71
1.72
1.73
1.74
1.75
1.76
1.77
1.78
1.79
1.8
1.81
1.82
1.83
1.84
1.85
1.86
1.87
1.88
1.89
1.9
1.91
1.92
1.93
1.94
1.95
1.96
1.97
1.98
1.99
2. PBC CONDITIONS OF APPROVAL PRIOR TO CO(S)
2.01 | Right Turn Lane North Approach | 2021-12-14 | 1242 | PBC Comments - Monitoring ENG-003b |  | WGI | AGC | 2023-06-16 |  | 25% | Work underway as of 05/19/2023, Asphalt completion target 06/29/2023 07/18/2023
2.02 | Median Landscaping at Jog Road | 2021-12-14 | 1242 | PBC Comments - Monitoring ENG-006b |  | WGI | AGC | 2023-06-23 |  | 95% | Final inspection to occur following completion of NB turn lane extension (expected by end of June 2023)
2.03 | Jog Road South Approach Left Turn Lane Extension | 2021-12-14 | 1242 | PBC Comments - Monitoring ENG-008B |  | WGI | AGC | 2023-06-16 |  | Not Started | Work to begin in conjunction with SB deceleration lane (item 2.01)
2.04 | Amenity Completion | 2021-12-14 | 1242 | PBC Comments - Monitoring PARKS-001 |  | WGI | AGC | 2023-04-14 |  | 25% | Currently tracking for on-time completion prior to 1st TCO application
2.05 | School Bus Shelter Completion | 2021-12-28 | 1228 | PBC Comments - Monitoring SCHOOL-002 |  | WGI | AGC | 2023-04-14 |  | 30% | Slab accessibility resolution provided to ADC and implemented in field, TPO complete, pending Stucco
3. DESIGN DEVELOPMENT
4. AHJ COORDINATION
4 | AHJ CLOSE-OUT REQUIREMENTS | 2023-04-18 | 752 | Close-Out Tracking Log (LINK) |  | AGC & ADC | AGC |  |  |  | Close-Out requirement tracking log linked in column 'E' of this log item for ease of access
4.09 | Clubhouse & Residential Building BDA Surveys | 2022-09-13 | 969 | Weekly Progress Call 09/13/2022 | [6 empty] | Dates listed are projected completion of window installation at each building
4.09(CH) | Clubhouse BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-02-06 |  | 75% | Report received from SLS noting no BDA required per survey results - pending direction on next steps from PBC rep
4.09(01) | Building 01 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-02-06 |  | 75% | Report received from SLS noting no BDA required per PBC FCC radio licencee - pending direction on next steps from PBC rep
4.09(12) | Building 12 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-02-15 |  | 0%
4.09(11) | Building 11 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-03-09 |  | 0%
4.09(10) | Building 10 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-03-19 |  | 0%
4.09(09) | Building 09 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-04-20 |  | 0%
4.09(08) | Building 08 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-05-11 |  | 0%
4.09(07) | Building 07 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-06-02 |  | 0%
4.09(06) | Building 06 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-06-12 |  | 0%
4.09(05) | Building 05 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-07-11 |  | 0%
4.09(04) | Building 04 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-07-27 |  | 0%
4.09(03) | Building 03 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-08-15 |  | 0%
4.09(02) | Building 02 BDA Survey | 2022-09-13 | 969 | Progress Schedule |  | ADC | AGC | 2023-08-25 |  | 0%
4.12 | PBC Closeout Procedures Clarification | 2023-01-09 | 851 | AGC Close-Out Tracking Log |  | AGC | AGC | 2023-03-31 |  | 50% | Coordination of close-out procedures underway with MTCI and PBC
5. ALTMAN INTERNAL COORDINATION ITEMS
5.13 | CIS Constructability Report | 2022-09-09 | 973 | CIS Constructability Report |  | ADC | ADC & AGC | 2022-07-29 |  | 75%
5.16 | Access Partnership Open Report Items | 2023-04-18 | 752 | Accessibility Report Tracking Log (LINK) |  | AGC | ADC & AGC | 2023-08-01 |  | ONGOING | Report tracking log linked in column 'E' of this log item for ease of access
5.17 | Fire Alarm Monitoring Agreement | 2023-05-15 | 725 | Email: MF to KN 05/15/2023 @ 12:07 PM |  | AGC | AMC | 2023-05-26 |  | 50% | Monitoring agreement required for FA programming and inspection sent to KN for execution
5.18 | Final Sign Package (Building & Directional) | 2023-06-16 | 693 | Review Meeting 06/16/2023 |  | AGC | ADC / AGC / AMC | 2023-06-30 |  | 75% | Additional language, clarification, AHJ requirements necessary to release Sign Jive for Building & Directional Package (Monument in fabrication)
6. CONSTRUCTION PROGRESS
0 |  |  | 45786
0 |  |  | 45786
7. CHANGE TRACKING
7.01 | PCO's Pending ADC Response | Date Submitted | 165.1451 | ← Aging of Current Open PCOs (Average) |  |  |  | Submitted + 30cd |  |  | Status of Work Related to PCO
PCO067 | CE#070 Drainage System Changes - West Perimeter Yard Drains | 2023-05-30 | 710 |  |  | ADC | ADC | 2023-06-20 |  | 50% | Pending - Not Proceeding
PCO069 | Shower Enclosures | 2023-06-20 | 689 | BF email to MF 06/08/2023 |  | ADC | ADC | 2023-07-11 |  | 50% | Pending - In Review
7.02 | PCO's Pending AGC Action | BIC Date | 44.3333 | ← Aging of Current Open PCOs (Average) |  |  |  | BIC + 15wd |  |  | Status of Work Related to PCO
PCO041 | RFI 48, Trash Compactor Drainage | 2023-02-17 | 812 |  |  | ADC | AGC | 2023-03-10 |  | 50% | Cost as submitted rejected by ADC 02/17/2023 - AGC to revisit cost with Impact for possible revision to PCO
PCO055r1 | 100% CD (Mechanical) | 2023-05-12 | 728 |  |  | ADC | ADC | 2023-06-02 |  | 50% | Response received from ADC, returned to Armstrong for proposed settlement - pending response
PCO066 | Subcontractor Cost Escalations - CB Structures | 2023-06-06 | 703 |  |  | ADC | ADC | 2023-06-27 |  | 35% | Rejected by ADC 06/05/2023 - revised cost to be submitted with additional information from CB Structures
CE#046 | Light Fixture Quantity Conflict | 2023-03-17 | 784 |  |  | ADC | AGC | 2023-04-07 |  | 25% | Review meeting with AGC & ADC scheduled for 05/30/2023 @ 8:00 AM
CE#100 | Pool Pavilion Landscape Change | 2023-03-14 | 787 |  |  | ADC | AGC | 2023-04-04 |  | 35% | Additional change on LP-2 included with CCD (remove 1 Royal Poinciana east of pool eqpt) - BF requested credit update from Amaro
CE#118 | Temp AC at Clubhouse | 2023-06-02 | 707 | Monthly OAC 06/02/2023 |  | ADC | AGC | 2023-06-23 |  | 50% | ROM of $15k/month approved by ADC 06/05/2023
CE#120 | Electric Room Doors at Bld Type 3B & 3B-FHA | 2023-06-08 | 701 | MTCI Hot Check Inspection |  | ADC | AGC | 2023-06-29 |  | 30% | AGC collecting all relevant pricing while proceeding with work to pass electrical hot check inspections required for meter release
CE#122 | Exterior Eyebrow Sealing and Finishing | 2023-06-27 | 682 |  |  | ADC | AGC | 2023-07-18 |  | 25% | AGC pricing finish at exterior eyebrows throughout project were no finish or sealing detail was provided
7.03 | PCO's on Hold | Date Submitted | 906 | ← Aging of Current Open PCOs (Average) |  |  |  | BIC + 15wd |  |  | Status of Work Related to PCO
PCO036r1 | AC Condenser Screening | 2022-11-15 | 906 | RFI 123 |  | ADC | ADC | 2022-12-27 |  | 50% | Pending - Not Proceeding, On-Hold, ADC to determine necessity at time of completion
CCD017r1 | Permit Revision 1 | 2022-11-22 | 899 | Email from MF 11/22/2022 |  | AGC | AGC | 2022-12-22 |  |  | Drawings inadequate for pricing. CCD enforcement pending issuance of coordinated drawings with all current updates.
8. CIVIL COMPLETION
8.01 | Off Site - Dry Detention (North PL) Remaining Vegetation | 2022-12-05 | 886 | RFI 179 / Sheets FRP-1 & FRP-2 |  | AGC | AGC | 2022-12-30 |  | 95% | Tree removal and grading complete - sod and fence to be installed for closure of item
8.03 | Off Site - Drainage at Plateau West of Deste Court | 2022-12-05 | 886 | RFI 176 / Sheet 30 |  | AGC | AGC | 2023-02-03 |  | 50% | Impact to explore existing FPL location and propose solution to conflict following completion of drainage work in item 8.02 above
8.04 | Off Site - Lake Bank Expansion & Tie-In to Existing Grade | 2022-12-05 | 886 | RFI 177 / Sheet 31 |  | AGC | WGI | 2023-01-04 |  | 80% | Fine grading in progress, stabalization expected to be complete by 06/30/2023. Meeting with Impact & ADC to be scheduled for cost resolution.
8.05 | Off Site - LWDD Canal Bank | 2022-11-02 | 919 | RFI 178 / Sheet 31 |  | AGC | WGI | 2022-12-30 |  | 65% | Signed permit transfer form sent from Lennar to WGI 01/18/2023, closure of item pending schedule of precon meeting and completion of work
8.07 | Off Site - Jog Road Drainage Structure S-103 | 2022-10-27 | 925 | Sheet 32 |  | AGC | WGI | 2022-11-26 |  | 50% | Work in progress with southbound deceleration lane construction
8.09 | Storm Drain Elevations on West Side of Compatibility Buffer | 2022-12-14 | 877 | Email from BF to TD |  | WGI | AGC | 2023-03-31 |  | 50% | Cost for work submitted to ADC under PCO067, work will not proceed without approval
CLOSED
This Update
PCO068 | PBC Permit Delay - PDI Claim | 2023-06-01 | 25 |  |  | ADC | AGC | 2023-06-22 | 2023-06-26 | 100% | Approved
Prior Updates
1.01 | Site Development Permit | 2021-10-11 | 351 | PBC Permit PR-2021-048696-0000 | PBC Approval | WGI | ADC | 2022-02-03 | 2022-02-19 | 100% | Approved and Issued on 02/19/2022, Sub-permits pending application
1.02 | Storm Drainage Permit | 2022-01-18 | 252 | PR-2022-003330-0000 | PBC Approval | WGI | ADC | 2022-02-10 | 2022-02-16 | 100% | No Sub Apps pending
1.03 | PBCWUD Permit (Pre-App Meeing) | 2021-12-28 | 174 | WUD #19-588 |  | WGI | PBCWUD | 2022-02-10 |  | 100% | All approvals received from PBCWUD as of 06/16/20222
1.03a | PBCWUD Submittals | 2021-12-14 | 287 | Submittal Log |  | WGI | WGI |  |  |  | Item closed to consolidate log - reference item 1.03
1.03b | Pre-App Meeting: Lift Station | 2021-12-28 | 174 | Email from TD on 03/22/2022 | PBCWUD Meeting Sign-in Sheet 06/16/2022 | WGI | WGI | 2022-02-10 | 2022-06-16 | 100% | Final Pre-App Meeting held on-site 06/16/2022, work approved to proceed
1.04 | MOT Permit | 2022-01-25 | 245 | AGC Submittal 02-760-013 | Email from TD to BF 04/18/2022 | WGI | AGC | 2022-02-13 | 2022-04-18 | 100% | Approved by PBC, pending payment of fees by ADC
1.03b | Pre-App Meeting: Water and Sewer | 2021-12-28 | 273 | Email from TD on 03/22/2022 | Pre-app meeting package | WGI | WGI | 2022-02-10 | 2022-04-11 | 100% | Pre-app meeting package to be distributed by TD
1.05 | Residential Building Permits | 2021-12-28 | 247 | Permit Tracking Log | PBC Issued Building Permits | WGI | PBC | 2022-05-13 | 2022-09-01 | 100% | All residential building permits issued by PBC
1.05a | Exterior Elevations per PBC Zoning | 2022-02-22 | 217 | Permit Tracking Log | Email from Susan Goggin to CJ 05/11/22 | ATL | ATL / ADC | 2022-04-13 | 2022-05-11 | 100% | Proposed elevation changes informally approved by PBC Zoning - revision to be submitted
1.06 | CH Building Permit | 2021-12-28 | 246 | Permit Tracking Log | PBC Issued Building Permits | WGI | ADC | 2022-06-12 | 2022-08-31 | 100% | CH permit issued by PBC
1.06a | Fire Sprinkler Drawings | 2022-04-12 | 168 | PCO008 Executed 04/12/2022 |  | AGC | Wayne | 2022-04-29 |  | 100% | 61G15 design provided by Wayne in August 2021
1.06a | Fire Sprinkler System Required | 2022-03-18 | 193 | WGI Comment Tracking Log |  | ADC | AGC | 2022-04-01 | 2022-04-05 | 100% | PBC will require fire sprinkler system - PCO submitted to ADC
1.07 | Amenity Buildings & Structures Permits | 2021-12-28 | 287 | Permit Tracking Log |  | WGI | AGC | 2022-06-12 | 2022-10-11 | 100% | All primary building permits received as of Bus Shelter issuance 10/11/2022
1.08 | PBC Cond. of Approval | 2021-12-14 | 287 | PBC Review Comments - Monitoring |  | WGI |  | 2022-06-08 |  | Pending
1.08a | Legal Lot of Record per Art. 11 of ULDC | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-002 |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | "Resolved" per PBC SDP Review Comments
1.08b | Right Turn Lane Nort Approach | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-003a |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | ROW Permits approved and transferred to ADC
1.08c | Public Road Drainage Easements | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-004 |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | "Resolved" per PBC SDP Review Comments
1.08d | Median Landscaping at Jog Road | 2021-12-14 | 266 | PBC Comments - Monitoring ENG-006a | Permit LA62075-0822 email from Sue Loyd | WGI |  | 2022-06-08 | 2022-09-06 | 100% | LA62075-0822 received 09/06/2022
1.08e | Median Landscaping at Jog Road Alternate Option | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-006d |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | Satisfied by item 1.08d (eng comment 006a)
1.08f | Jog Road South Approach Left Turn Lane Extension | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-008a |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | ROW Permits approved and transferred to ADC
1.08g | Easement Crossing D Este Court | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-010b |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | "Resolved" per PBC SDP Review Comments
1.08h | DRC Recorded with PBC | 2021-12-14 | 287 | PBC Comments - Monitoring PLANNING-001 |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | "Resolved" per PBC SDP Review Comments
1.08i | Drainage Study and Required Easements | 2021-12-14 | 287 | PBC Comments - Monitoring ENG-005b |  | WGI |  | 2022-06-08 | 2021-12-14 | 100% | "Resolved" per PBC SDP Review Comments
1.08j | Approved Zoning Plan | 2022-02-08 | 231 | PBC Zoning Resolution - Engineering (9) |  | WGI |  | 2022-06-08 |  | 100% | Pending update/clarification from WGI
1.08k | Attainability of Workforce Units | 2022-02-08 | 231 | PBC Zoning Resolution - Planning (1) |  | WGI |  | 2022-06-08 | 2022-03-01 | 100% | Documents sent to WGI 02/22/2022 - JP closing loop
1.08l | Workforce Compliance Reporting | 2022-02-08 | 231 | PBC Zoning Resolution - Planning (2) |  | NA | NA | NA | NA | 100% | AMC responsible
1.08m | Compatibility Buffer Landscape Design | 2022-03-22 | 189 | Email from J.Catalo(PBC) to RG 03/22/2022 | PCO009 | DS | WGI | 2022-04-15 | 2022-04-13 | 100% | Revision to be submitted with Elevation changes - PCO009 executed 04/13/2022
1.09 | Swimming Pool Permit Application | 2022-02-14 | 225 | Base Line Schedule 02/03/2022 |  | AGC | AGC | 2022-05-25 |  | VOID | 30 day Health review + 60(+) PBC Permit Review
1.12a | Precast Perimeter Wall Permit | 2022-03-04 | 207 | Email from BF to JP w/ S&S Engineering |  | WGI | WGI | 2022-03-14 |  | 100% | Permit app number recorded by WGI - not in PBC Portal
1.12b | Entry Feature | 2022-03-14 | 273 | Permit Tracking Log | Permit Issuance B-2022-034702-0000 | WGI | AGC | 2022-11-07 | 2022-12-12 | 100% | Permit Issued by PBC Building
1.12c | Fence, Entry Gates, and Columns | 2022-03-14 | 443 | Permit Tracking Log |  | AGC | ADC | 2023-06-02 | 2023-05-31 | 100% | Change of Contractor application submitted to PBC - Pending Fee Payment by ADC
1.12d | Trash Enclosure | 2022-03-14 | 197 | Permit Tracking Log | PR-2022-009363-0000 | WGI | WGI | 2022-10-30 | 2022-04-18 | 100% | Submitted with Maintenance Building
1.12e | Swimming Pool (app submittal) | 2022-02-14 | 225 | Permit Tracking Log |  | AGC | PBC | 2022-05-25 | 2022-05-19 | 100% | Permit app submitted 05/19/2022
1.12e-1 | Aquadynamics Submit Engineered Drawing to HD | 2022-02-21 | 218 | Aquadynamics / FPL Drawings |  | AGC | Aquadynamics | 2022-03-04 | 2022-03-11 | 100% | Revised drawings received 03/11/2022 incorrect
1.12f | Site Fence | 2022-03-14 | 161 | Permit Tracking Log |  | WGI | AGC | 2022-11-15 | 2022-08-15 | 100% | Fence permit issued 08/15/2022
1.12g | Vehicular Entry Gates | 2022-03-14 | 239 | Permit Tracking Log |  | WGI | McNamara | 2022-11-07 |  | 50% | Submitted with Entry Gate Columns (now "Entry Gates and Columns") item 1.12c
1.12h | Emergency Vehicle Gate & Jog Road Fence | 2022-03-14 | 443 | Permit Tracking Log |  | WGI | McNamara | 2022-11-07 | 2023-05-31 | 100% | Pending Fee payment - BF notified MA 02/28/2023
1.12j | Dog Park | 2022-03-14 | 42 | Permit Tracking Log |  | WGI | PBC | 2022-10-31 | 2022-04-25 | 100% | Submitted, to be tracked in permit section as open permit application
1.12k | Pool Deck | 2022-03-14 | 42 | Permit Tracking Log |  | WGI | PBC | 2022-09-21 | 2022-04-25 | 100% | Submitted, to be tracked in permit section as open permit application
1.12l | Access Control | 2022-03-14 | 422 | Permit Tracking Log |  | WGI | AGC | 2022-10-04 | 2023-05-10 | 100% | CH Access Control permit approved and issued by PBC 05/10/2023
1.12m | Jog Road Fence, Vehicle Gates, & 1 Pedestrian Gate | 2023-05-30 | 1 | Permit Tracking Log |  | AGC | ADC | 2023-06-02 | 2023-05-31 | 100% | Change of Contractor application submitted to PBC - Pending Fee Payment by ADC
1.13 | Precast Perimeter Wall Permit | 2022-03-04 | 125 | Email from BF to JP w/ S&S Engineering |  | WGI | AGC | 2022-08-17 | 2022-07-07 | 100% | Issued to AGC 07/07/2022
1.14 | Site Plan Ammendment - Permit Revision | 2022-04-19 | 210 | Weekly Progress Call Minutes 04/19/2022 |  | WGI | WGI | 2022-06-12 |  | VOID | Item consolidated under "1.24, Permit Revision" for tracking as of 11/15/2022
1.15 | Pool Pavilion Structural - Permit Revision | 2022-05-02 | 143 | Pool Pavilion Construction Documents | Active Pool Pavilion Permit | ATL | McNamara | 2022-07-12 | 2022-09-22 | 100% | Closed following issuance of permit 09/22/2022
1.16 | Electrical Site - Permit Revision (Remove FPL Note) | 2022-04-27 | 202 | BF email to AR 04/27/2022 |  | Feller | Feller | 2022-06-12 |  | VOID | Item consolidated under "1.24, Permit Revision" for tracking as of 11/15/2022
1.17 | SWPPP Permit App | 2022-05-05 | 145 | BF email to MA 05/05/2022 | Email from J.Kiper re: approval | ADC | ADC | 2022-05-20 | 2022-07-11 | 100% | Permit approved and issued
1.18 | Swimming Pool | 2022-02-14 | 267 | Permit Tracking Log | Pool Permit Documents | AGC | AGC | 2022-08-26 | 2022-11-07 | 100% | Permit issued by PBC 11/07/2022
1.19 | Pool Deck Permit | 2022-04-25 | 161 | Permit Tracking Log |  | WGI | PBC | 2022-07-24 | 2022-10-03 | 100% | Issued by PBC
1.2 | Dog Park | 2022-04-25 | 333 | Permit Tracking Log |  | WGI | AGC | 2022-10-31 | 2023-03-24 | 100% | Activated by PBC
1.21 | MOT Permits | 2022-07-13 | 47 | Permit Tracking Log |  | WGI | AGC | 2022-08-18 |  | 100% | All MOT Permit Docs Received by AGC
1.22 | Landscape & Irrigation Permit Private Provider Review | 2022-08-22 | 36 | PBC Permit Review Comments | CCD014 | WGI | ADC | 2022-09-16 | 2022-09-13 | 100% | CCD014 issued by MF via email 09/14/2022
1.26 | Roofing Permits | 2023-01-12 | 96 | PBC ePBZ Portal |  | AGC | MTCI | 2023-02-17 | 2023-04-18 | 100% | All building permits issued
3.01 | Current Drawings, Sent to AGC for Coordination | 2022-01-11 | 259 | Meeting Minutes OAC 3, 01/11/022 |  | ADC | ADC | 2022-02-09 | 2022-02-08 | 100% | Current submitted/approved for permit received from WGI
3.02 | CAD Files | 2022-01-11 | 259 | CAD Receipt Schedule |  | Design Team | ATL | 2022-02-11 | 2022-02-01 | 100%
3.03 | Site Plan Ammendment | 2022-01-18 | 252 | JP Email 01/14/2022 |  | WGI | WGI | 2022-02-08 |  | 100% | Closed for re-assignment to permit item 1.14
3.04 | Unit Interior Doors | 2022-01-20 | 250 | OAC 006 Meeting Minutes | OAC 006 Meeting Minutes | AGC | ADC |  |  | 100% | 1 Panel Shaker Doors (Interior and Entry) Per LT & DS
3.04 | Constructability Review and Plan Changes | 2022-02-25 | 214 | BF Email to ADC 02/25/2022 |  | AGC | AGC | 2022-03-04 |  | VOID | Item closed in anticipation of 100% CD's week of 03/07/2022
3.05 | Conformed Drawing Sets | 2022-02-24 | 215 | RFI Review Meeting 02/24/2022 |  | Design Team | ATL | 2022-03-03 |  | VOID | Item closed in anticipation of 100% CD's week of 03/07/2022
3.06 | 100% CD Issue | 2022-03-03 | 208 | RFI Review Meeting 03/03/2022 |  | Design Team | AGC / ADC | 2022-03-03 |  | 95% | 100% CDs Issued 05/16/2022 - CCD instructs RFQs to be withheld until Permits Approved
3.06a | 100% CD CAD Files | 2022-03-03 | 208 | RFI Review Meeting 03/03/2022 |  | ATL | ATL | 2022-03-03 |  | Pending | To be included with CCD Issuance
3.06b | 100% CD Landscape Drawings | 2022-03-28 | 183 |  |  | DS Boca | DS Boca | 2022-04-15 | 2022-04-04 | 100% | Received - Pending CCD from ADC
3.07 | Civil Design Conflicts | 2022-02-25 | 214 | Email from Impact Site to AGC 02/25/2022 | Email from TD to BF 05/26/2022 | WGI | WGI | 2022-03-11 | 2022-05-26 | 100% | Approval of proposed structure revisions received via email from TD
3.07a | Flap Gate Design Conflict | 2022-03-24 | 187 | Email from BF to TD 03/24/2022 | Approval Email from TD 04/08/2022 | WGI | WGI | 2022-04-08 | 2022-04-08 | 100% | Duck Bill Valve accepted by PBC
3.07c | AT&T Conflict @ Jog Road | 2022-04-14 | 166 | RC email to AT&T 04/15/2022 |  | AGC | AT&T | 2022-04-28 |  |  | closed on 04/25/2022 for reassignment to item 6.05
3.08 | Residential Bldg Control Line Drawings | 2022-03-07 | 204 | Email from RC to CJ 03/07/2022 | CJ Email w/Drawings 04/26/2022 | ATL | ATL | 2022-04-08 | 2022-04-26 | 100% | Unit control lines added to drawings per RC examples sent via email
3.09 | Water Submeter Repeaters - Electrical Revision | 2022-05-11 | 139 | BF Email to ADC 05/05/2022 | CCD 009 issued 07/26/2022 | ADC | Feller | 2022-07-01 | 2022-07-06 | 100% | CCD issued with requested revision documents
3.1 | Mail Kiosk Revision to Remove Parcel Room & Lockers | 2022-06-21 | 98 | Weekly Progress Call Minutes 06/21/2022 | CCD 010 issued 07/26/2022 | ADC | ATL | 2022-07-21 | 2022-07-26 | 100% | Niche to remain for future use by AMC, no changes to construction documents
3.11 | Architectural vs Structural Plan Conflicts | 2022-02-17 | 271 | RFI #20 3B-FHA Building Plan Conflicts |  | ATL | ATL | 2022-07-01 |  | VOID | Item consolidated under "1.24, Permit Revision" for tracking as of 11/15/2022
3.12 | Light Fixture Package and Plan Coordination | 2022-07-08 | 81 | Email from DS to BF 07/08/2022 | Approved Submittals and PCO 017 | ATL | ATL | 2022-08-07 | 2022-08-02 | 100% | Revised site fixture received 08/02/2022
3.13 | Site EV Charger Building Electrical Revisions | 2022-08-24 | 167 | Email from BF to MA re EV Charger CCD |  | ATL | ATL / ADC | 2022-09-30 | 2023-02-07 | 100% | Captured in "Permit Revision 1" item 1.25 above - to be tracked there until revision approval
3.14 | Lift Station Slab Revision | 2022-10-10 | 43 | RFI 142: Site/Civil Lift Station Discrepancy | Revised sheet C-63 | WGI | WGI | 2022-09-30 | 2022-11-22 | 100% | Revision to sheet C-63 pending, add pad dimensions required for PBC permit prior to LS completion
3.15 | SEER2 Electrical Conflict | 2022-08-12 | 200 | RFI #69 | RFI 200 | ATL | AGC | 2023-02-10 | 2023-02-28 | 100% | Pending EOR Revision to Panel Schedules and COR from PDI for 30 AMP breakers at all residential unit AHU feeds
3.16 | Unit EV Charger Electrical Revision | 2023-01-13 | 46 | BF Discussion with MA On-Site | Weekly Progress Call 02/28/2023 | ATL | Feller | 2023-02-10 | 2023-02-28 | 100% | Not proceeding per LT - to be installed by AMC as needed
3.17 | Unit Type D2-FHA and D3-FHA Kitchen Ceilings | 2023-01-20 | 18 | Unit Mock-Up Review | MF email to BF 02/07/2023 | ADC | ADC | 2023-02-03 | 2023-02-07 | 100% | Direction received from ADC 02/07/2023 via MF email - final markup of Type 3B-FHA RCP changes to be submitted for record
3.18 | Bus Shelter Electrical & Lighting | 2023-02-02 | 81 | BF Email to MF |  | ADC | ADC | 2023-02-24 | 2023-04-24 | 100% | Revision approved and issued by PBC
3.19 | Fixture Type E Conflict | 2023-02-02 | 76 | AGC to ADC Email String |  | ADC | ADC | 2023-02-24 | 2023-04-19 | 100% | PO released to vendor by ADC
3.2 | Exterior Building Paint Scheme | 2023-01-20 | 96 | Building 1 Framing Walk-Through | CCD 020 received 02/23/2023 | ADC | AGC | 2023-03-24 | 2023-04-26 | 100% | Paint colors and general scheme approved by ADC - per building type to be monitored as progress continues
3.21 | Clubhouse Life Safety Plan Revision per PBCFD | 2023-04-19 | 38 | Email from BF to CJ 04/19/2023 @ 7:36 AM |  | ATL | ATL | 2023-05-12 | 2023-05-27 | 100% | Letter provided by ATL accepted by PBCFD to resolve open comment - no further action required
4.01 | Project Addressing - USPS | 2022-01-11 | 429 | Meeting Minutes OAC 3, 01/11/022 | Email from USPS to AGC | AGC | AGC | 2022-07-01 | 2023-03-16 | 100% | Mailbox approval received 03/16/2023
4.02 | FPL Design | 2020-10-14 | 713 | CC Email to FPL 10/14/2020 |  | AGC | AGC | 2022-02-11 | 2022-03-10 | 100% | Complete - materials requested, relocation PCO submitted to ADC
4.02a | Two FPL Poles North of Proposed Entrance | 2022-03-02 | 209 | BF Email to JP & TD 03/02/2022 |  | WGI | WGI | 2022-03-11 | 2022-03-11 | 100% | Included in FPL Pole Relocation Scope
4.03 | FPL Relocation Invoices | 2022-02-04 | 235 | BF Email to MA 02/04/2022 |  | AGC | ADC | 2022-02-11 | 2022-03-10 | 100% | Confirmed payment received by FPL 03/10/2022
4.04 | Comcast Service Agreement | 2021-09-23 | 397 | MA Email to Comcast 09/23/2021 |  | ADC | ADC | 2022-09-30 | 2022-10-25 | 100% | Agreement executed per JW
4.04a | Comcast SOW Conflict | 2022-02-17 | 222 | Comcast Service Agreeement |  | ADC | ADC | 2022-03-25 | 2022-03-14 | 100% | Confirmed to be resolved by M.Connel w/ Comcast
4.05 | Comcast Construction Design | 2022-01-10 | 260 | JW Email to BF 01/10/2022 | FINAL_JB0000901117_FLITE00500_ALTIS BLUE LAKE_EPON_V3 | AGC | AGC | 2022-09-30 | 2022-06-13 | 100% | Design received from Comcast 06/13/2022
4.06 | FPL Relocation Easement | 2022-05-25 | 43 | Easement docs delivery to MA by AW | Recorded FPL Easement Confirming Email | ADC | ADC | 2022-06-17 | 2022-07-07 | 100% | Easement received by FPL and confirmed by Deborah Olawuni via email 07/07/2022
4.07 | PBCWUD Close-Out Documents | 2022-09-08 | 236 | TD Email to MA 09/08/2022 |  |  |  | 2023-01-31
Water Distribution System
4.07(1) | Preliminary As-Built Submittal | 2022-09-08 | 236 |  |  | WGI | WGI | 2023-01-06 |  | 80% | 1st round comments received from PBCWUD via WGI 03/23/2023 - generating responses for resubmittal week of 04/03/2023 at latest
4.07(2) | Chlorinate and Bac-T Sample Water Main | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-02-05 |  | 25% | System chlorinated week ending 12/16/2022. Bac-T samples pending completion and preliminary approval of as-built drawings.
4.07(3) | FDEP Construction Water Request | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-02-05 |  | 0% | To include approved as-builts and bac-t results less than 60 days old (1-3 days expected approval)
4.07(4) | Valve Openings and Jumper Removals | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-02-15 |  | 0% | Following FDEP Approval (Hydrants active at this time)
4.07(5) | Flush and Pressure Test Water Main | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-02-25 |  | 0%
4.07(6) | Final Certification Submittal to PBCWUD | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-03-07 |  |  | All forms/sample documents provided by TD via email 09/08/2022 at 3:12 PM (3-10 day expected review)
4.07(6a) | Consent and Joinder | 2022-09-08 | 236 | Email from BF to MA |  | WGI | ADC | 2023-01-06 |  | 0% | Believed by ADC to be NA - WGI to Confirm
4.07(6b) | Indemnification Agreement | 2022-09-08 | 236 | Email from BF to MA |  | WGI | ADC | 2023-01-06 |  | 0% | Believed by ADC to be NA - WGI to Confirm
4.07(6c) | Indemnity Agreement | 2022-09-08 | 236 | Email from BF to MA |  | WGI | ADC | 2023-01-06 |  | 0% | Believed by ADC to be NA - WGI to Confirm
4.07(6d) | Lien Affidavit | 2022-09-08 | 236 | Email from BF to MA |  | WGI | ADC | 2023-01-06 | 2023-01-18 | 90% | Provided to WGI by ADC 01/18/2023 - pending submittal to PBCWUD
4.07(6e) | Testing & Startup Reports | 2022-09-08 | 236 | Email from BF to MA |  | WGI | AGC | 2023-02-28 |  | 0% | To be prepared in concert with flush and pressure test
4.07(6f) | Utility Easement | 2022-09-08 | 236 | Email from BF to MA |  | WGI | AGC | 2023-01-06 | 2023-01-18 | 90% | Provided to WGI by ADC 01/18/2023 - pending submittal to PBCWUD
4.07(6g) | Bill of Sale | 2022-09-08 | 236 | Email from BF to MA |  | WGI | AGC | 2023-01-06 | 2023-01-18 | 90% | Provided to WGI by ADC 01/18/2023 - pending submittal to PBCWUD
4.07(7) | PBCHD Clearance for Final Release | 2022-09-08 | 236 |  |  | WGI | AGC | 2023-04-21 |  | 0% | 3-5 day expected review
4.08 | AC Condenser Screening | 2022-08-30 | 56 | JP email to LT 08/30/2022 | DS Boca response to RFI 123 | ADC | AGC | 2022-10-21 | 2022-10-04 | 100% | Item closed, to be tracked via PCO036 above
4.1 | LWDD Precon Meeting | 2022-11-02 | 42 | TD Email to LWDD 11/02/2022 | Moved to section 8. Civil Completion | WGI | WGI | 2022-12-09 |  | VOID | Item closed as of 12/06/2022 update, to be tracked via item 8.05
4.11 | FPL Agreement Documents | 2022-12-09 | 97 | Email from BF to ADC 12/09/2022 |  | AGC | ADC | 2023-01-27 | 2023-03-16 | 100% | All documents submitted and transformers energized as of 03/16/2023
4.13 | Civil Conveyance Clarifications | 2023-04-12 | 20 | BF email to TD 04/12/2023 @ 6:28 AM |  | WGI | WGI | 2023-04-21 | 2023-05-02 | 100% | Remaining items to be tracked via item 4.00 above and associated log
5.01 | Revised ADC Submittal Review Matrix | 2022-02-04 | 235 | On Site Conversation between MA & BF | ADC Submittal Schedule | ADC | ADC | 2022-02-11 | 2022-02-07 | 100% | Schedule received by AGC via email from MA 02/07/2022
5.02 | AGC Submittal Schedule | 2022-02-08 | 231 | OAC 007 Meeting Minutes |  | AGC | ADC / Design Team | 2022-02-25 |  | 100% | No comments received by requested date - Item closed
5.03 | Entry Feature Tile Selection (CCD needed) | 2022-02-09 | 223 | DS Email 02/09/2022 | CCD 016 | ADC | ADC | 2022-02-18 | 2022-09-20 | 100% | MF issued CCD 016 09/20/2022
5.04 | List of Premium Units (LVT) | 2022-02-16 | 125 | RG Email 02/16/2022 | Email from JW to BF w/ Unit Premium Analysis | ADC | AGC | 2022-03-04 | 2022-06-21 | 100% | List of premium units received from JW 06/21/2022 - tracking to continue via PCO 015
5.05 | Drainage Permit Plans and CAD Files (CCD needed) | 2022-02-16 | 223 | Approval of Storm Drainage Permit | File transfer email from TD | ADC | ADC | 2022-02-25 | 2022-03-24 | 100% | Received from TD - item now tracked via Change Events Log
5.06 | Feller Ground Floor Revisions (CCD needed) | 2022-02-17 | 222 | A.Robinson Email 02/17/2022 |  | ADC | ADC | 2022-02-25 |  | VOID | Item closed in anticipation of 100% CD's week of 03/07/2022
5.07 | Site Development Permit Plans (CCD needed) | 2022-02-19 | 220 | Approval of Site Development Permit |  | ADC | ADC | 2022-02-25 |  | VOID | Item closed in anticipation of 100% CD's week of 03/07/2022
5.08 | Model Unit Selection and Design | 2022-02-22 | 217 | CCD004 - Pending Revision | Responde to RFI 18 | ADC | AGC | 2022-05-27 | 2022-05-25 | 100% | CCD004 04/19/2022 - further clarifications on SOW required, expected mid May per MF
5.1 | Lighting Dynamic Package Procurement | 2022-03-31 | 180 | Email from RG to ADC 03/31/2022 |  | ADC | ADC | 2022-04-15 | 2022-05-16 | VOID | Item closed, to be tracked via PCO017 above
5.1 | Swimming Pool Tile Procurement | 2022-06-14 | 238 | Weekly Progress Call 06/14/2022 Minutes |  | ADC | ADC | 2022-07-29 | 2023-02-07 | 100% | Lagassee to provide lane marker tile at no additional cost
5.14 | Mockups - Framing and MEP Devices: Unit Types D1, D2, D3 | 2022-12-13 | 38 | Construction Progress Schedule |  | AGC | AGC | 2023-01-20 | 2023-01-20 | 100% | Mock-up review completed 01/20/2023 - items to be addressed have been added above
5.15 | Mockups - Framing & MEP Devices: Unit Types A1, A2, & C2-C4 | 2023-01-30 | 14 | Unit Mock-Up Review |  | AGC | AGC | 2023-02-03 | 2023-02-13 | 100% | Coordinated and documented via markups in email correspondence between BF and MF on 02/13/2023
OCO001 | Reconciliation of PCO's approved in Feb & March 2022 | 2022-03-28 | 183 | Email: RY to ADC 03/28/2022 @ 12:22PM | Executed OCO 001 | ADC | ADC | 2022-04-27 | 2022-04-01 | 100% | Proceeding per Approved PCO's included
OCO002 | April 2022 PCO Reconciliation | 2022-04-26 | 154 |  | Executed OCO 002 | ADC | AGC | 2022-05-26 | 2022-06-06 | 100%
OCO003 | Owner Change Order 03, July PCO Reconciliation | 2022-08-04 | 18 |  |  | ADC | ADC | 2022-09-03 | 2022-08-11 | 100% | Approved OCO 003 08/11/2022
PCO004 | Remove & Reinstall Viny Fence @ Drainage | 2022-03-02 | 209 | Change Event #17 | Executed PCO004 | ADC | ADC | 2022-04-01 | 2022-03-24 | 100% | Proceeding
PCO005 | Jog Road Median Landscaping | 2022-03-09 | 202 | Change Event #26 | Executed PCO005 | ADC | ADC | 2022-04-08 | 2022-03-24 | 100% | Proceeding
PCO006 | FPL Primary Redesign and Relocation | 2022-03-09 | 202 | Change Event #14 | Executed PCO006 | ADC | ADC | 2022-04-08 | 2022-03-24 | 100% | Proceeding
PCO007 | Primary Power and Communications Site Installation | 2022-04-06 | 174 | Email from RG to LT/MA 03/31/2022 | Executed PCO007 | AGC | ADC | 2022-05-06 | 2022-04-12 | 100% | Approved - Proceeding
PCO008 | Clubhouse Fire Sprinkler System | 2022-04-06 | 174 | PBC Fire Permit Review Comments | Executed PCO008 | AGC | ADC | 2022-05-06 | 2022-04-12 | 100% | Approved - Proceeding
PCO009 | Compatibility Buffer Planting Requirements | 2022-04-06 | 174 | PBC Zoning Resolution | Executed PCO009 | AGC | ADC | 2022-05-06 | 2022-04-12 | 100% | Approved - Proceeding
PCO011r1 | PBCWUD Delay | 2022-04-25 | 183 | Construction Schedule |  | ADC | ADC | 2022-05-25 |  | VOID | To be revised with updated cost and time information
PCO013 | Window Type R-C Height Increase to 72" | 2022-04-29 | 151 | Joint Submittal Review Meeting 04/29/2022 | Rejected PCO returned by ADC | ADC | ADC | 2022-05-29 | 2022-05-26 | 100% | Verbal direction received from LT, NOT PROCEEDING - ADC to return PCO
PCO014 | Jog Road Hedge Height | 2022-04-29 | 151 | Weekly Progress Call 04/26/2022 Minutes | Executed PCO 014 | ADC | ADC | 2022-05-29 | 2022-06-17 | 100% | Approved - Proceeding
PCO015r1 | LVT Throughout Residential Units | 2022-07-11 | 43 | MF Email Request 04/27/2022 | Rejected PCO returned by ADC | ADC | ADC | 2022-08-10 | 2022-08-23 | 100% | Rejected - Not Proceeding
PCO016 | Water Submeter Repeaters | 2022-05-11 | 139 | BF Email to ADC 05/05/2022 | Executed PCO 016 | ADC | ADC | 2022-06-10 | 2022-06-17 | 50% | Approved - Proceeding
PCO017r1 | ADC Light Fixture Package | 2022-05-12 | 39 | RG Email to ADC 04/08/2022 | Executed PCO017r1 06/09/2022 | ADC | ADC | 2022-06-11 | 2022-06-17 | 100% | Approved - Proceeding
PCO018r1 | Jog Road Utility Conflicts - Soft Dig | 2022-06-06 | 14 | BF Email to LT 04/22/202 | Executed PCO018r1 6/09/2022 | ADC | ADC | 2022-07-06 |  | 100% | Approved - Proceeding
PCO019 | Organic Soil Content Exploraiton and Hauling | 2022-06-07 | 78 | BF Email to ADC 03/02/2022 | Approved PCO returned by ADC | ADC | ADC | 2022-07-07 | 2022-08-24 | 100% | Approved
PCO020r1 | SignJive Quote Changes | 2022-06-16 | 67 | Email from MA to BF 02/23/2022 |  | ADC | ADC | 2022-07-16 | 2022-08-03 | 100% | Approved PCO received 08/04/2022
PCO021 | Amenity Appliance Specification Discrepancy | 2022-09-07 | 975 | Email from MF to BF 07/05/2022 |  | ADC | ADC | 2022-10-07 | 2022-09-29 | 100% | VOID
PCO022 | Fixture Type SL Mounting Detail | 2022-07-11 | 43 | RFI 042 | Voided PCO returned by ADC | ADC | ADC | 2022-08-10 | 2022-08-23 | 100% | Voided - Not Proceeding (SL Fixture removed from project by EOR)
PCO023r2 | Exterior Elevations per PBC Zoning | 2022-08-09 | 15 | PBC Zoning Visual Impact Comments | Approved PCO returned by ADC | ADC | ADC | 2022-09-08 | 2022-08-24 | 100% | Approved - Proceeding
PCO025 | Replace PBC Traffic Fiber Due to Damage | 2022-08-09 | 15 | BF Email to LT 06/13/2022 | Approved PCO returned by ADC | ADC | ADC | 2022-09-08 | 2022-08-24 | 100% | Approved - Proceeding
PCO030 | Exterior Elevation Changes per PBC (Painting) | 2022-09-07 | 23 |  |  | ADC | ADC | 2022-10-07 | 2022-09-30 | 100% | Approved
PCO031 | Residential Unit Balcony Waterproofing | 2022-09-07 | 975 |  |  | ADC | ADC | 2022-10-07 | 2022-09-29 | 100% | Approved
PCO032r1 | Water Submeter Repeaters - Electrical Requirements | 2022-09-08 | 74 |  |  | ADC | ADC | 2022-10-08 | 2022-11-21 | 100% | Pending - Not Proceeding (r1 submitted 11/01/2022)
PCO033r1 | Site Lighting Revision | 2022-10-24 | 106 | PBC Approved Site Lighting Plan |  | ADC | AGC | 2023-02-18 | 2023-02-04 | 100% | PCO Approved
PCO034 | Pool Bubblers at Sun Shelf | 2022-11-01 | 7 | Pool Permit Drawings | Executed PCO 034 | ADC | AGC | 2022-12-01 | 2022-11-03 | 100% | Approved
PCO035 | Permit Delay Claim | 2022-11-14 | 39 |  |  | ADC | ADC | 2022-12-23 |  | 100% | Approved, OCO006 Created 12/23/2022
PCO037r3 | 100% CD (Electrical) | 2022-12-05 | 106 |  |  | ADC | ADC | 2023-01-16 | 2023-03-21 | 100% | Approved
PCO038r1 | SEER2 Code Change | 2022-11-17 | 36 |  |  | ADC | ADC | 2022-12-23 |  | 100% | Approved, Armstrong SCO001 created 12/27/2022,
PCO039 | Tucci Site Furnishings | 2022-11-21 | 15 |  |  | ADC | ADC | 2022-12-21 | 2022-12-06 | VOID | ADC to procure Stingray Shades for AGC Install - Credit PCO for Shade Sails to be submitted
PCO039r1 | Tucci Site Furnishings | 2023-01-03 | 70 |  |  | ADC | ADC | 2023-01-24 | 2023-03-14 | 100% | Approved
PCO040 | LP Tank Size Change | 2022-11-29 | 32 |  |  | ADC | ADC | 2022-12-29 | 2022-12-31 | 50% | Approved
PCO042 | Entry Sign Tile | 2023-01-18 | 20 |  |  | ADC | ADC | 2023-02-17 | 2023-02-06 | 100% | Approved
PCO043 | Electrical Meter Socket Procurement | 2023-01-31 | 17 |  |  | ADC | ADC | 2023-03-02 | 2023-02-17 | 100% | Approved and returned to AGC 02/17/2023
PCO044 | EM Battery Backups for CH Light Fixtures | 2023-01-31 | 43 |  |  | ADC | ADC | 2023-03-14 | 2023-03-15 | 100% | Approved
PCO045r1 | Unit Framing Changes - Bld Types 1A, 1B, 2, & 3B-FHA | 2023-04-04 | 20 |  |  | ADC | AGC | 2023-05-16 | 2023-04-24 | 100% | Approved - to be included in upcoming OCO009 (ABC SCO003 created 05/01/2023)
PCO046 | Surveying Services for Civil Design Conflicts | 2023-02-08 | 41 |  |  | ADC | ADC | 2023-03-22 | 2023-03-21 | 100% | Approved
PCO047 | Clubhouse Parapet Stucco Bands | 2023-02-10 | 7 |  |  | ADC | ADC | 2023-03-24 | 2023-02-17 | 100% | Approved and returned to AGC 02/17/2023
PCO048r1 | Sheet C-31, Add MH-1B & MH-64 | 2023-02-14 | 35 |  |  | ADC | ADC | 2023-03-07 | 2023-03-21 | 100% | Approved
PCO049r1 | Sheet C-32, Jog Road Drainage Changes | 2023-04-13 | 11 | Rev0 submitted 03/02/2023 |  | ADC | AGC | 2023-05-04 | 2023-04-24 | 100% | Approved - to be included in upcoming OCO009 (Impact SCO010 created 05/01/2023)
PCO050 | Unit Framing Changes - Interior Doors | 2023-02-21 | 14 |  |  | ADC | ADC | 2023-03-14 | 2023-03-07 | 100% | Rejected
PCO051 | Unit Framing Changes - Walls & Ceilings @ Type 1A Typ Units | 2023-02-21 | 808 |  |  | ADC | AGC | 2023-03-14 | 2023-04-11 | VOID | VOID - Consolidated with PCO045r1
PCO052 | S-17 & S-18 Curb Conflicts | 2023-03-03 | 32 |  |  | ADC | ADC | 2023-03-24 | 2023-04-04 | 100% | Approved - SCO issued 04/10/2023
PCO054 | Unit Interior Door Changes - Privacy Doors | 2023-03-09 | 792 |  |  | ADC | ADC | 2023-03-30 | 2023-03-21 | 100% | Approved
PCO056 | Building Type 4 Exterior Faux Columns | 2023-03-29 | 2 |  |  | ADC | AGC | 2023-04-19 | 2023-03-31 | 100% | Approved
PCO057r1 | Adverse Weather Delays as of 03/27/2023 | 2023-04-04 | 20 |  |  | ADC | AGC | 2023-04-25 | 2023-04-24 | 100% | Approved - to be included in upcoming OCO009
PCO058 | Access Control & CCTV Changes | 2023-03-29 | 2 |  |  | ADC | AGC | 2023-04-19 | 2023-03-31 | 100% | Approved
PCO059 | Pavilion Grill Emergency Shut Offs | 2023-03-29 | 2 |  |  | ADC | ADC | 2023-04-19 | 2023-03-31 | 100% | Approved
PCO061 | Secondary Size Conflict | 2023-05-22 | 8 |  |  | ADC | ADC | 2023-06-12 | 2023-05-30 | 100% | Approved, PDI SCO010 issued 06012023
PCO062 | Exterior Paint Mock-Ups | 2023-05-23 | 7 |  |  | ADC | AGC | 2023-06-13 | 2023-05-30 | 100% | Approved
PCO063 | Clubhouse Changes by Development | 2023-05-23 | 7 |  |  | ADC | ADC | 2023-06-13 | 2023-05-30 | 100% | Approved
PCO064 | Garage Exhaust Vent Caps | 2023-05-26 | 7 |  |  | ADC | ADC | 2023-06-16 | 2023-06-02 | 100% | REJECTED
PCO065r1 | Unit Entry Smart Locks Latch Access Control System | 2023-06-06 | 7 | CCD022 |  | ADC | ADC | 2023-06-27 | 2023-06-13 | 100% | Approved - Proceeding with Access Control Change, Not Proceeding with Entry Lock Change
CE#099 | Unit Entry Smart Locks | 2023-03-14 | 34 |  |  | ADC | AGC | 2023-04-04 | 2023-04-17 | VOID | CCD022 recalled and void by ADC via MF email 04/17/2023
5.11 | LVT Throughout Residential Units | 2022-04-27 | 153 | MF Email Request 04/27/2022 |  | AGC | ET | 2022-05-04 | 2022-05-09 | 100% | Item Closed - tracking via PCO015 as of 05/09/2022 log
5.11* | Site Lighting Head Specification (Pending PCO Resolution) | 2022-06-17 | 165 | BF email to ADC/Feller 06/17/2022 |  | ADC | ADC | 2022-07-01 | 2022-11-29 | 50% | Closed as of 11/29/2022, to be tracked under PCO033 until fully resolved
5.12 | NGBS Checklist Items | 2022-08-22 | 92 | J.Languell Email to AGC/ADC re: Checklist | Closed per MA as of 11/15/2022 | ADC | ADC | 2022-09-30 | 2022-11-15 | 100% | No anticipated scope or cost change
5.14 | Pool - Sun Shelf Bubblers | 2022-09-12 | 51 | MA Phone Call with BF 09/12/2022 | Revision received from Aquadynamics | ADC | AGC | 2022-10-21 | 2022-11-02 | 100% | Closed via approval of PCO034 11/02/2022 and submittal of revised drawings by Lagasee for permit revision
6.01 | Mulch at Water Main Trench | 2022-02-28 | 211 | Bill Needle Email to Lennar 03/10/2022 | BL_De-muckingObservation_03222022 | AGC | Nutting | 2022-03-18 |  | 100% | See report at link in "CLOSURE DOCUMENT" cell
6.02 | Lennar Force Main Conflict w/ BL Drainage | 2022-03-31 | 165 | BF email to BN 04/04/2022 |  | WGI | WGI | 2022-04-08 |  | 75% | Work believed to be complete per Jackson, confirm with WGI
6.04 | PBC Traffic Conduit Coordination | 2022-04-18 | 162 | BF email to TD 04/18/2022 |  | AGC | AGC | 2022-05-02 |  |  | Closed for re-assignment to subtask of item 6.05 above
6.05a | PBC Traffic Conduit Coordination | 2022-04-18 | 162 | BF email to TD 04/18/2022 |  | AGC | AGC | 2022-05-13 |  | 100% | Coordination complete - work proceeding according to progress schedule
6.05b | Energy Transfer Gas Transmission Line | 2022-03-22 | 189 | RC email to WGI 03/22/2022 |  | WGI | AGC | TBD | 2022-05-09 | VOID | Item closed - no conflict identified with proposed work following exploration
6.05c | AT&T Conflict @ Jog Road | 2022-04-14 | 166 | RC email to AT&T 04/15/2022 | Meeting Minutes 06/08/2022 | WGI | WGI | 2022-05-13 | 2022-06-03 | 100% | Check by ADC to be returned/canceled. Direct burial lines do not belong to AT&T.
6.05d | Crown Castle Emergency Services Fiber | 2022-04-22 | 122 | Sunshine Locates email to RC 04/22/2022 |  | WGI | WGI | 2022-05-06 | 2022-08-16 | 100% | Crown Castle relocated 08/16/2022
6.05e | Forcemain Installation Safety Concerns | 2022-10-25 | 42 | Progress Call 10/25/2022 | Moved to section 8. Civil Completion | AGC | WGI | 2022-12-02 |  | VOID | Item closed as of 12/06/2022 update, to be tracked via item 8.06
6.05f | Drainage Structure S-103 Conflict w/ Existing AT&T | 2022-10-27 | 40 | WGI Site Visit 10/27/2022 | Moved to section 8. Civil Completion | WGI | AGC | 2022-11-11 |  | VOID | Item closed as of 12/06/2022 update, to be tracked via item 8.07
6.06 | FPL Conflict at Existing Catch Basin NW Corner | 2022-03-22 | 189 | Email from BF to FPL 03/22/2022 |  | AGC | FPL | 2022-04-15 | 2022-08-15 | 100% | Conflict resolved by FPL, item closed
6.07 | Lennar Water Main Certification | 2022-05-11 | 149 | Email from BF to TD 05/11/2022 |  | Lennar | AGC | 2022-05-18 | 2022-10-07 | 100% | Certified for construction water as of 10/07/2022
6.08 | Existing Trees within PL @ FPL Substation Boundary | 2022-05-19 | 131 | Email from BF to MA 05/19/2022 |  | AGC | AGC | 2022-06-03 | 2022-06-22 | 100% | Trees to remain in place, berm to be constructed around existing trees.
8.02 | Off Site - Drainage at Southwest Corner Near Fountains Dr. | 2022-12-05 | 158 | RFI 175 / Sheet 29 |  | AGC | AGC | 2023-02-28 | 2023-05-12 | 100% | Drainage assemblies installed in accordance with plan despite discrepancies in existing conditions as directed by WGI
8.06 | Off Site - Jog Road Force Main Crossing | 2022-10-25 | 202 | Sheet 32 |  | AGC | AGC | 2022-11-24 | 2023-05-15 | 100% | Forcemain install and wet tap complete as of 05/03/2023 - Pressure test passed 05/15/2023
8.08 | Off Site - Northwest Lake Bank Tie-In to Existing Grade | 2022-12-05 | 162 | RFI 180 / Sheet 31 |  | AGC | WGI | 2022-12-30 | 2023-05-16 | VOID | Item consolidated with item 8.04, "Lake Bank Expansion & Tie-In to Existing Grade" above
Formulas:
DAYS ELAPSED = IF([DATE IDENTIFIED]=""," ",IF(AND([DATE IDENTIFIED]<>"",[COMPLETION DATE]=""),TODAY()-[DATE IDENTIFIED],[COMPLETION DATE]-[DATE IDENTIFIED]))
DAYS ELAPSED = IF(ISBLANK([COMPLETION DATE]),TODAY()-[DATE IDENTIFIED],[COMPLETION DATE]-[DATE IDENTIFIED])
DUE = [DUE, row above]+10
DUE = WORKDAY([DATE IDENTIFIED],15,0)
Button 67
Note on B108: PRIOR TO CO PLEASE ACKNOWLEDGE THAT YOU HAVE READ: ENG-003.b The Property Owner shall construct a right turn lane north approach on Jog Road at the project entrance road. This construction shall be concurrent with the paving and drainage improvements for the site. Any and all costs associated with the construction shall be paid by the Property Owner. These costs shall include, but are not limited to, utility relocations and acquisition of any additional required right-of-way. Construction shall be completed prior to the issuance of the first Certificate of Occupancy. Please contact Land Development Division: Scott Cantor, Assistant Director at 561-684-4090
Note on B109: ENG-006.b The Property Owner shall design, install, and perpetually maintain median landscape within the median of all abutting right of way of Jog Road. This landscaping and irrigation shall strictly conform to the specifications and standards for the County's Only Trees, Irrigation, and Sod (OTIS) program. Additional landscaping beyond OTIS requires Board of County Commissioner's approval. Median landscaping installed by the Property Owner shall be perpetually maintained by the Property Owner, his successors and assigns, without recourse to Palm Beach County, unless the Property Owner provides payment for maintenance as set forth in Paragraph c and d below. All installation of the landscaping and irrigation shall be completed prior to the issuance of the first certificate of occupancy. Please contact Land Development Division: Scott Cantor, Assistant Director at 561-684-4090
Note on B110: ENG-008.b The Property Owner shall fund the construction plans and the construction to lengthen the existing left turn lane south approach on Jog Road at the Project entrance road. This turn lane shall be lengthened to a minimum 250 feet in length plus 50 foot paved taper. This construction shall be concurrent with the paving and drainage improvements for the site. Any and all costs associated with the construction shall be paid by the Property Owner. These costs shall include, but are not limited to, utility relocations and acquisition of any additional required right-of-way. Construction shall be completed prior to the issuance of the first Certificate of Occupancy. Please contact Land Development Division: Scott Cantor, Assistant Director at 561-684-4090
Note on B111: PARKS-001 No more than 64 Certificates of Occupancy for the residential units shall be issued until the recreational improvements have been completed in their entirely and open for use and accessible to the residents, unless a phasing plan for completion of the required reaction area is agreed to and approved by the Parks and Recreation Department Please contact :PBC PARKS and RECREATION ADMIN, Planning: Jean Matthews, Senior Planner, is at 561-966-6652, Daniel Duenas, Planner is at 561-966-6659.
Note on B112: SCHOOL - 002 Prior to the issuance of the first Certificate of Occupancy (CO), the 10 feet by 15 feet school bus shelter shall be constructed by the Property Owner in a location and manner acceptable to the Palm Beach County School Board. Provisions for the bus shelter shall include, at a minimum, a covered area, continuous paved pedestrian and bicycle access from the subject property or use, to the shelter. Maintenance of the bus shelter shall be the responsibility of the residential Property Owner. Please contact PBC SCHOOL DISTRICT, Planning & Intergov Relations, Div of Facilities Mgt: Michael Owens, Senior Planner at 561-882-1938

## Help (hidden)
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html