## GCs & GRs
STADIUM ENCLAVE APARTMENTS RENO
| Construction |  |  | Activity |  | Start | Finish | Days | Weeks | Months | % Time | Remarks
|  |  |  | Construction |  | 2026-03-01 | 2026-11-30 | 274 | 39.1429 | 9.1333
|  |  |  | Close Out |  | 2026-11-30 | 2026-12-30 | 30 | 4.2857 | 1
|  |  |  | General Conditions |  | General Req. - Field Office |  | General Req. |  | Total
| Description | Qty. | U | Unit | Const. | Unit | General | Unit | General |  |  |  | CUSTOMIZED LABOR RATES | LABOR RATE FY 2025 *Updated 09.26.24
|  |  |  | Cost | Cond. | Cost | Req. | Cost | Req.
| Field Labor - Construction | [8 empty] | 1177437.4971
| Project Executive | 39.1429 | wks | 2554.2 | 99978.6857 |  |  |  |  | 99978.6857 | 30% |  | 212.85 | 212.85
| Senior Project Manager | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 176.41 | 176.41
| Project Manager - Level 3 | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 162.46 | 162.46
| Project Manager - Level 2 | 39.1429 | wks | 5948 | 232821.7143 |  |  |  |  | 232821.7143 | 100% |  | 148.7 | 148.7
| Project Manager - Level 1 | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 127.26 | 127.26
| Project Administator | 39.1429 | wks | 3591.2 | 140569.8286 |  |  |  |  | 140569.8286 | 100% |  | 89.78 | 89.78
| Project Accountant | 39.1429 | wks | 2316.8 | 90686.1714 |  |  |  |  | 90686.1714 | 50% |  | 115.84 | 115.84
| Assistant Project Manager | 39.1429 | wks | 4467.6 | 174874.6286 |  |  |  |  | 174874.6286 | 100% |  | 111.69 | 111.69
| Superintendent - Level 3 | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 177.87 | 177.87
| Superintendent - Level 2 | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 149.3 | 149.3
| Superintendent - Level 1 | 39.1429 | wks | 4887.6 | 191314.6286 |  |  |  |  | 191314.6286 | 100% |  | 122.19 | 122.19
| Assistant Superintendent | 39.1429 | wks | 3235.6 | 126650.6286 |  |  |  |  | 126650.6286 | 100% |  | 80.89 | 80.89
| Assistant Superintendent | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 80.89 | 80.89
| Assistant Superintendent | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 80.89 | 80.89
| Quality Control Manager | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 138.96 | 138.96
| Foreman | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 56.06 | 56.06
| Accounting | 39.1429 | wks | 926.72 | 36274.4686 |  |  |  |  | 36274.4686 | 20% |  | 115.84 | 156.52
| VDC Manager | 39.1429 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 138.68 | 138.68
| Safety Supervisor/Inspector | 39.1429 | wks | 2152.8 | 84266.7429 |  |  |  |  | 84266.7429 | 50% |  | 107.64 | 107.64
| Field Labor - Close Out | [8 empty] | 139556.3143
| Project Executive | 4.2857 | wks | 2809.62 | 12041.2286 |  |  |  |  | 12041.2286 | 33% |  | 212.85 | 212.85
| Senior Project Manager | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 176.41 | 176.41
| Project Manager - Level 3 | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 162.46 | 162.46
| Project Manager - Level 2 | 4.2857 | wks | 5948 | 25491.4286 |  |  |  |  | 25491.4286 | 100% |  | 148.7 | 148.7
| Project Manager - Level 1 | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 127.26 | 127.26
| Project Administator | 4.2857 | wks | 3591.2 | 15390.8571 |  |  |  |  | 15390.8571 | 100% |  | 89.78 | 89.78
| Project Coordinator | 4.2857 | wks | 2316.8 | 9929.1429 |  |  |  |  | 9929.1429 | 50% |  | 115.84 | 115.84
| Assistant Project Manager | 4.2857 | wks | 4467.6 | 19146.8571 |  |  |  |  | 19146.8571 | 100% |  | 111.69 | 111.69
| Superintendent - Level 3 | 4.2857 | wks | 7114.8 | 30492 |  |  |  |  | 30492 | 100% |  | 177.87 | 177.87
| Superintendent - Level 2 | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 149.3 | 149.3
| Superintendent - Level 1 | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 122.19 | 122.19
| Assistant Superinterndent | 4.2857 | wks | 3235.6 | 13866.8571 |  |  |  |  | 13866.8571 | 100% |  | 80.89 | 80.89
| Foreman | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 56.06 | 56.06
| Accounting | 4.2857 | wks | 926.72 | 3971.6571 |  |  |  |  | 3971.6571 | 20% |  | 115.84 | 156.52
| VDC Manager | 4.2857 | wks | 0 | 0 |  |  |  |  | 0 | 0% |  | 138.68 | 138.68
| Safety Supervisor/Inspector | 4.2857 | wks | 2152.8 | 9226.2857 |  |  |  |  | 9226.2857 | 50% |  | 107.64 | 107.64
| Field Office - Contractor | [8 empty] | 82720
| Field Office Set Up / Removal - Double Wide | 1 | ea |  |  | 16000 | 16000 | ` |  | 16000
| Field Office - Double Wide | 5 | mos |  |  | 3500 | 17500 |  |  | 17500
| Field Office Set Up / Removal - Single Wide | 0 | ea |  |  | 15958 | 0 |  |  | 0 |  | WILLSCOT 4/16/2024 (36x10 mobile office)
| Field Office - Single Wide | 0 | mos |  |  | 1732 | 0 |  |  | 0 |  | WILLSCOT 4/16/2024 (36x10 mobile office)
| Field Office Set Up / Removal - Connex | 5 | mos |  |  | 1371 | 6855 |  |  | 6855 |  | WILLSCOT 20' COMBO W/10' OFFICE
| Field Office - Conex | 5 | mos |  |  | 573 | 2865 |  |  | 2865 |  | WILLSCOT 20' COMBO W/10' OFFICE
| Connect Telephone Lines | 1 | ea |  |  | 2000 | 2000 |  |  | 2000
| Telephone/Internet | 5 | mos |  |  | 250 | 1250 |  |  | 1250
| Cellular Telephones | 0 | mos |  |  | 0 | 0 |  |  | 0 |  | In labor rates
| Furniture | 1 | ls |  |  | 2500 | 2500 |  |  | 2500
| Office Supplies | 5 | mos |  |  | 250 | 1250 |  |  | 1250
| Drinking Water | 5 | mos |  |  | 200 | 1000 |  |  | 1000
| Janitor Supplies/Cleaning | 5 | mos |  |  | 50 | 250 |  |  | 250
| Software Charge | 0% | % |  |  | 64806874 | 0 |  |  | 0 |  | .25% of GMP Total
| Computers | 1 | ls |  |  | 25000 | 25000 |  |  | 25000
| Printers | 1 | ls |  |  | 500 | 500 |  |  | 500
| Copy Machine | 5 | mos |  |  | 250 | 1250 |  |  | 1250
| Alarm System | 5 | mos |  |  | 0 | 0 |  |  | 0
| Installation Office Equip. | 0 | ls |  |  | 250 | 0 |  |  | 0
| Storage Trailers Set Up / Removal | 2 | ea |  |  | 1000 | 2000 |  |  | 2000 |  | willscot 40' trailer
| Storage Trailers | 5 | mos |  |  | 500 | 2500 |  |  | 2500 |  | Rate - $1200 ea. per month
| Temporary Utilities | [8 empty] | 76351
| Temp. Electrical Service | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by elect sub
| Temp. Electrical - Const. Phase | 0 | mos |  |  |  |  | 8000 | 0 | 0 |  | In Hardcosts
| Temp. Electrical - Operate Phase | 0 | mos |  |  |  |  | 8000 | 0 | 0 |  | In Hardcosts
| Temp. Wiring & Lighting | 0 | sf |  |  |  |  | 0 | 0 | 0 |  | by elect sub
| Temporary Water - Service | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by plumb sub
| Temporary Water | 0 | mos |  |  |  |  | 1000 | 0 | 0
| Temporary Toilets | 5 | mos |  |  |  |  | 1750 | 8750 | 8750
| Temporary Toilet Set Up / Removal | 7 | ea |  |  |  |  | 93 | 651 | 651
| Temporary Washing Station | 0 | mos |  |  |  |  | 407 | 0 | 0
| Temporary Washing Station Set Up / Removal | 0 | ea |  |  |  |  | 93 | 0 | 0
| Temporary Holding Tanks | 5 | mos |  |  |  |  | 750 | 3750 | 3750
| Temporary Ventilation | 0 | ls |  |  |  |  | 0 | 0 | 0
| Temporary Cooling | 5 | mos |  |  |  |  | 0 | 0 | 0
| Equipment | [7 empty] | 0 | 0
| Small Tools | 19.5 | mos |  |  |  |  | 1500 | 29250 | 29250
| Equipment Rental | 19.5 | mos |  |  |  |  | 1600 | 31200 | 31200
| Engineering Instruments | 0 | ls |  |  |  |  | 1000 | 0 | 0
| Security | [7 empty] | 0 | 0
15000 | Temporary Fence - 6' Post Driven w/ windscreen | 0 | lf |  |  |  |  | 8 | 0 | 0 |  | In Hardcosts
| Temporary Fence - 8' Post Driven w/ windscreen | 0 | lf |  |  |  |  | 13 | 0 | 0
| Temporary Fence - 6' Panels w/ windscreen | 0 | lf |  |  |  |  | 6 | 0 | 0
| Temporary Fence - 8' Panels w/ windscreen | 0 | lf |  |  |  |  | 7 | 0 | 0
| Temporary Fence - Gates 8'x24' | 0 | ea |  |  |  |  | 1500 | 0 | 0 |  | In Hardcosts
15000 | Temporary Fence Maintain | 0 | mos |  |  |  |  | 150 | 0 | 0 |  | In Hardcosts
| Security Service | 0 | wks |  |  |  |  | 1233 | 0 | 0 |  | In Hardcosts
| Additional Safety Material/Modifications | 0 | ls |  |  |  |  | 10000 | 0 | 0
15000 | Protection Floor & Roof Openings | 0 | ls |  |  |  |  | 2500 | 0 | 0
| Protection Existing Floors & Walls | 0 | ls |  |  |  |  | 1500 | 0 | 0
| Protection Service Elevator | 0 | ls |  |  |  |  | 500 | 0 | 0
15000 | Temporary Enclosures | 0 | ls |  |  |  |  | 5000 | 0 | 0
| Temporary Ladders | 0 | ls |  |  |  |  | 0 | 0 | 0
15000 | Building Barricades | 0 | ls |  |  |  |  | 5000 | 0 | 0
15000 | Site Barricades | 0 | ls |  |  |  |  | 5000 | 0 | 0
| Fire Protection | 5 | mos |  |  |  |  | 500 | 2500 | 2500
| First Aid | 5 | mos |  |  |  |  | 50 | 250 | 250
| Drug Testing | 0 | ea |  |  |  |  | 0 | 0 | 0
| Cleaning | [8 empty] | 20354.2857
| Trash Removal - 10yd dumpsters | 0 | wks |  |  |  |  | 350 | 0 | 0
| Trash Removal - 20yd dumpsters | 0 | wks |  |  |  |  | 400 | 0 | 0
| Trash Removal - 30yd dumpsters | 0 | wks |  |  |  |  | 2500 | 0 | 0 |  | In Hardcosts
| Trash Removal - Field Offices | 39.1429 | wks |  |  |  |  | 0 | 0 | 0
17300 | General Building Cleaning | 39.1429 | wks |  |  |  |  | 520 | 20354.2857 | 20354.2857
| Final Building Clean | 361970 | sf |  |  |  |  | 0 | 0 | 0 |  | In Hardcosts
| Services | [8 empty] | 750
13200 | CMP Schedule - Set Up | 0 | ls |  |  |  |  | 10000 | 0 | 0 |  | Call Assaf Newmark (Spectrum Consulting) to confirm 404-819-4663
13200 | CPM Schedule - Updates (Standard Reports) | 0 | mos |  |  |  |  | 1650 | 0 | 0 |  | Call Assaf Newmark (Spectrum Consulting) to confirm 404-819-4664
13200 | CPM Schedule - Updates (Bifurcated Reports) | 0 | mos |  |  |  |  | 300 | 0 | 0 |  | Call Assaf Newmark (Spectrum Consulting) to confirm 404-819-4665
13233 | Progress Photos Bldg. - Ground | 5 | mos |  |  |  |  | 50 | 250 | 250
13233 | Progress Photos Bldg. - Aerial | 5 | mos |  |  |  |  | 100 | 500 | 500
| Video - Existing Conditions | 0 | ls |  |  |  |  | 2500 | 0 | 0
13233 | Video - Owner O&M Demo. | 0 | ls |  |  |  |  | 500 | 0 | 0
| Legal | 0 | ls |  |  |  |  | 0 | 0 | 0
| Drawings | [8 empty] | 10750
| As Built Survey | 0 | ls |  |  |  |  | 1000 | 0 | 0
10550 | As Built Drawings | 0 | ls |  |  |  |  | 500 | 0 | 0
| Plan/Copy Expense | 1 | ls |  |  | 10000 | 10000 |  |  | 10000
| Postage - USPS | 5 | mos |  |  | 75 | 375 |  |  | 375
| Postage - Fed-X | 5 | mos |  |  | 75 | 375 |  |  | 375
| Testing | [8 empty] | 0
| Concrete Testing | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by owner
| Steel Testing | 0 | ea |  |  |  |  | 0 | 0 | 0 |  | by owner
| Special Inspectors | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by owner
| Permits | [8 empty] | 5500
| Building Permits | 5 | ls |  |  |  |  | 1000 | 5000 | 5000 |  | Sub Trades Only
| Impact Fees | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by owner
| Trailer Permits | 1 | ea |  |  |  |  | 500 | 500 | 500
| Off Site Permits | 0 | ls |  |  |  |  | 0 | 0 | 0 |  | by owner
| Travel | [8 empty] | 19250
| Airfare | 5 | mos |  |  |  |  | 2000 | 10000 | 10000
| Hotel | 5 | mos |  |  |  |  | 1000 | 5000 | 5000
| Per Diem | 5 | mos |  |  |  |  | 850 | 4250 | 4250
| Other | 5 | mos |  |  |  |  | 0 | 0 | 0
| Other | [8 empty] | 7500
| Project Sign | 5 | ea |  |  |  |  | 1500 | 7500 | 7500
| Temporary Parking | 0 | ls |  |  |  |  | 0 | 0 | 0
| Legal Notices | 0 | ea |  |  |  |  | 0 | 0 | 0
| Total |  |  |  | 1316993.8114 |  | 93470 |  | 129705.2857 | 951450.3486
[8 empty] | Total GCs |  | 1316993.8114 | 144196.4027
[8 empty] | Total GRs |  | 223175.2857 | 24435.2503
[8 empty] | Total GCs & GRs |  | 1540169.0971 | 168631.653 | per month
$-